Introduction to Software Engineering

Project Proposal & Plan

UniEvent is a university event management platform integrating event approval, ticketing, payment confirmation, QR-based attendance, and event monitoring. This document presents the project's vision, scope, proposed solution, development plan, risks, and collaboration approach.

Software Engineering Department

Faculty of Information and Technology

University of Science

Table of Contents

Revision History	1

Objectives	2

1 Member Contribution Assessment	4

2 Vision	5

2.1 Preliminary Problem Statement	5

2.2 Product Position Statement	14

2.3 Stakeholders and Users	16

2.4 Scope and Key Features	21

3 Proposed Solution	27

3.1 Preliminary Architecture	27

3.2 Technology Stack	27

3.3 Hardware and Operating Environment	28

4 Project Plan	30

4.1 Process and Phase Gates	30

4.2 Work Breakdown Structure (WBS)	31

4.3 Estimation	35

4.4 Schedule	48

4.5 Roles and Responsibilities	51

4.6 Human Resources and Cost Estimate	54

5 Risk Management	56

6 Tools & Collaboration Setup	61

7 AI Usage Log	66

Project Proposal & Plan

UniEvent - Team 07

# Revision History

| Version | Date | Changed by | Section(s) | Change |
| --- | --- | --- | --- | --- |
| 0.1 | 19/10/2026 | Thái Quang Huy | 2.1–2.4 | First draft of the Vision: problem statement, position statement, stakeholders and MoSCoW feature list F01–F16. |
| 0.1 | 19/10/2026 | Trần Vũ Anh Kiệt | 3.1–3.3 | First draft of the C4 System Context diagram, technology stack with reasons and operating environment. |
| 0.1 | 19/10/2026 | Lê Nguyễn Quốc Học | 4.1–4.6 | First draft of phase gates, WBS Levels 1–3, estimates, Gantt chart, roles and cost estimate. |
| 0.1 | 19/10/2026 | Nguyễn Văn Minh | 5, 6 | First draft of the risk register R1–R9 and the tools and collaboration setup. |
| 0.2 | 20/10/2026 | Lê Nguyễn Quốc Học | 2 | Reviewed the Vision; review comments resolved by the section owner. |
| 0.2 | 20/10/2026 | Nguyễn Văn Minh | 3 | Reviewed the Proposed Solution; review comments resolved by the section owner. |
| 0.2 | 20/10/2026 | Trần Vũ Anh Kiệt | 4 | Reviewed the Project Plan; review comments resolved by the section owner. |
| 0.2 | 20/10/2026 | Thái Quang Huy | 5, 6 | Reviewed Risk Management and Tools; review comments resolved by the section owner. |
| 0.3 | 20/10/2026 | Thái Quang Huy | 2.1, 2.3 | Added actor-specific problems, the actor × feature matrix and the key-data stewardship table. |
| 0.3 | 20/10/2026 | Thái Quang Huy | 7 | Consolidated member AI usage entries into the AI Usage Log. |
| 0.4 | 21/10/2026 | Lê Nguyễn Quốc Học | 2.4, 3.3 | Limited PA5 payments to one authorised payOS channel with a mock adapter for CI. |
| 0.4 | 21/10/2026 | Lê Nguyễn Quốc Học | 4.3–4.6 | Reconciled capacity, contributor hours, target schedule and costs. |
| 0.4 | 21/10/2026 | Nguyễn Văn Minh | 5, 6 | Aligned R2–R4 and CI deadlines with Section 4; recorded the 21/10 setup verification. |
| 1.0 | 21/10/2026 | Thái Quang Huy | 2.1–2.4 | Split the problem and position statements per problem and per user; restored organisation administration in F01; added an actor column to the feature list. |
| 1.0 | 21/10/2026 | Lê Nguyễn Quốc Học | 4.2–4.6 | One executing owner per work package; added WBS 2.2.8 and 5.2.13; calendar dates; corrected the Table 6 total. |
| 1.0 | 21/10/2026 | Lê Nguyễn Quốc Học | All | Integrated, froze and submitted PA1; committed the PDF and source to /pa/PA1. |

# Objectives

This document focuses on the following topics:

- Completing the Project Proposal & Plan document with the following sections:

  - Vision

  - Proposed Solution

  - Project Plan

  - Risk Management

  - Tools & Collaboration Setup

- Including an AI usage log for this phase

- Understanding the Project Proposal & Plan document.

# Member Contribution Assessment

Contributions must add up to 100%. For PA1 document sections, evidence may include the shared Google Docs version history, review comments and the PA1 GitHub Project issue. Individual section pull requests are not required by the team’s co-editing workflow.

| ID | Name | Role(s) | Contribution (%) | Evidence |
| --- | --- | --- | --- | --- |
| 24127044 | Lê Nguyễn Quốc Học | Team lead / PM; Developer | 25% | PA1 issue #31; W3 assignment/review record |
| 24127177 | Thái Quang Huy | Business analyst; Developer | 25% | PA1 issue #29; W3 assignment/review record |
| 24127196 | Trần Vũ Anh Kiệt | Designer / Architect; Developer | 25% | PA1 issue #30; W3 assignment/review record |
| 24127205 | Nguyễn Văn Minh | Tester / DevOps; Developer | 25% | PA1 issue #32; W3 assignment/review record |
|  | Total |  | 100% |  |

Contributions total 100%. All four members confirmed the 25% allocation on 21/10/2026 in the Discord #decisions channel. Evidence per member: the section owned and the section reviewed in W3-Status.md, PA1 issues #29–#32, the Google Docs version history and the Revision History above.

Assignment and review record: W3-status.md

# Vision

## Preliminary Problem Statement

Business context

Student clubs, the Youth Union (Đoàn Thanh niên), and the Student Association (Hội Sinh viên) organise various campus events, including workshops, seminars, competitions, performances, and volunteer activities. Based on the team's initial experience, some of these events use free or low-cost tickets, while attendance records may contribute to students' conduct-score assessments (điểm rèn luyện), depending on university regulations. These practices will be further validated with student organisers during the requirements phase (PA2).

Current way of working

In our experience, an event is often run with a chain of unconnected tools. The organising committee sends the event plan to the Youth Union by e-mail or on paper. After approval, students register through a Google Form and pay by bank transfer with a free-text transfer description. Organisers reconcile bank statements against form responses by hand and then e-mail confirmations one by one. At the door, volunteers look names up in a spreadsheet or on a printed list. After the event, the attendance list is retyped and sent to the Youth Union as evidence for conduct score.

Problems. The main challenge is not the absence of individual tools for registration, payment, approval or attendance, but the fragmentation of these activities across disconnected systems: information is copied and reconciled by hand, which costs effort, causes errors and gives nobody a view of the whole event life cycle. The six problems below state who is affected and what a successful solution must achieve.

| P1 | Manual payment reconciliation |
| --- | --- |
| The problem of | matching bank transfers with free-text descriptions against Google Form responses by hand |
| affects | club organisers who handle registration and finance, and students who pay for tickets |
| the impact of which is | slow confirmation, missing, duplicated or mismatched payments, confirmations e-mailed one by one, and disputes about whether a student has paid |
| a successful solution would | create a VietQR payment link per reservation, confirm payment from a verified payOS webhook, issue exactly one ticket per paid order and flag exceptions for review (F05–F06) |

| P2 | Unreliable ticket validation |
| --- | --- |
| The problem of | admitting attendees by searching spreadsheets or printed lists, without a centrally validated one-time ticket |
| affects | check-in volunteers, organisers and attendees waiting at the entrance |
| the impact of which is | queues at the door, admission with forwarded screenshots or duplicate entries, and inconsistent attendance records |
| a successful solution would | issue signed QR tickets and validate them on the server from a phone browser, rejecting invalid and used tickets and recording check-in and check-out separately (F06–F07) |

| P3 | Opaque event approval |
| --- | --- |
| The problem of | sending event plans to the Youth Union or Student Association by e-mail or on paper |
| affects | organisers who submit events and the officers who approve them |
| the impact of which is | organisers cannot see the status of a request, officers keep no searchable history of decisions and reasons, and events are delayed by follow-up messages |
| a successful solution would | provide an in-system submission and approval queue with approve, reject-with-reason and request-changes decisions and a complete decision history (F02–F03) |

| P4 | Weak attendance evidence |
| --- | --- |
| The problem of | collecting attendance on sign-in sheets and retyping it after the event |
| affects | attendees whose conduct score depends on it, organisers who report it and officers who verify it |
| the impact of which is | incomplete, hard-to-verify records, conduct-score appeals that are hard to settle, and repeated retyping work |
| a successful solution would | record attendance from QR check-in and check-out, export it as CSV (F07–F08) and optionally prepare draft conduct-score evidence for bulk review (F09) |

| P5 | No real-time view of the event |
| --- | --- |
| The problem of | having no single live view of ticket sales, payments and check-ins |
| affects | organisers and their event leads |
| the impact of which is | capacity and staffing decisions based on outdated spreadsheets, with overselling or empty seats discovered too late |
| a successful solution would | show tickets sold, revenue and check-in rate in real time with CSV export (F08), backed by atomic capacity control (F05) |

| P6 | Unmanaged organisations and privileges |
| --- | --- |
| The problem of | sharing form ownership, spreadsheets and payment details informally, with no register of organisations and their organisers |
| affects | the system administrator, organisers, approvers and every attendee whose personal data is collected |
| the impact of which is | the wrong people can edit or export participant data, nobody can show who granted access, and approvers cannot tell which club a submitter represents |
| a successful solution would | let administrators register organisations, grant organiser and approver roles scoped to an organisation, lock accounts and inspect an audit log, while organisers assign check-in staff to their own events (F01) |

Evidence. These observations come from the first-hand experience of our team lead, Lê Nguyễn Quốc Học, a member of the Student Volunteer Team (Đội Sinh viên tình nguyện) who has helped organise several of its activities and attended many other university events. He confirms that the steps above describe how such activities are run today. We treat them as preliminary domain knowledge, not as statistical evidence about all student organisations. To reduce reliance on a single organisation, we will validate key workflow assumptions through discussions with additional student organisers and review publicly available event information where relevant during PA2 (WBS 2.1.2). We also plan to ask the Student Volunteer Team to pilot UniEvent.

Actor-specific problems and value (initial hypotheses; PA2 interviews must validate differences across organisations)

| Actor / user group | Current task / data | Initial pain point | Problems | Planned UniEvent value | Validation status |
| --- | --- | --- | --- | --- | --- |
| Student attendee | Find an event; register; transfer the fee; show proof of attendance | Registration, payment and ticket confirmation span unconnected tools; attendance evidence may be lost. | P1, P2, P4 | One reservation, one verified ticket, visible attendance result (F05–F07). | Team experience only; interview students in PA2. |
| Club organiser | Submit an event; manage capacity, orders and the on-site team | Manual approval tracking, reconciliation and attendance reporting; no live status. | P1, P3, P4, P5 | Event workflow, ticket configuration, payment status, check-in staff assignment, dashboard and CSV (F01–F06, F08). | Confirm approval, refund and reconciliation variants with organisers. |
| Check-in volunteer | Validate tickets at the venue gate | Spreadsheet lookup is slow; duplicate admission is hard to detect. | P2 | Phone scanner limited to assigned events; server-side atomic validation; separate check-in and check-out (F07). | Test Android/iPhone, low connectivity and concurrent scanners. |
| Youth Union / Student Association approver | Review proposals from their unit; audit prior decisions | Decisions and reasons are fragmented and hard to audit. | P3, P4 | Approval queue for their unit, reasoned decisions and history (F03); optional attendance review (F09). | Verify delegated authority and approval stages with officers. |
| System administrator | Register organisations; grant privileged roles; resolve payment exceptions | Organisations and their organisers are recorded nowhere; access to forms, sheets and exports is shared informally. | P6 | Organisation register, scoped role grants, account lock and audit log (F01); exception resolution records (F06). | Confirm administration operations and minimum audit scope in PA2. |

Proposed solution

UniEvent is a web platform that connects the whole event life cycle. Organisers create an event and submit it for approval inside the system; Youth Union / Student Association officers approve, reject or request changes. Once an event is published, students reserve tickets, which are held for 15 minutes while they pay with any banking app through a VietQR payment link created by the payOS gateway. payOS notifies UniEvent through a signed webhook, and UniEvent issues a signed QR ticket and e-mails it to the student. Free tickets are issued without payment. At the venue, volunteers scan tickets with a phone browser; used or invalid tickets are rejected instantly, and organisers follow sales and check-in on a real-time dashboard. As an optional (Should-have) extension, check-in and check-out data can be turned into conduct score claims that officers approve in bulk.

Objectives and success criteria

The team's preliminary targets will be refined into functional acceptance criteria (WBS 2.2.1–2.2.3) and measurable non-functional requirements and business rules (WBS 2.2.4) during PA2. Test cases will be designed in PA4 and executed in PA5.

| Objective | Preliminary target | How it will be verified |
| --- | --- | --- |
| No manual payment reconciliation | For a valid and successfully matched payment, one ticket is created within 60 seconds after receipt of a verified payOS webhook, and e-mail delivery is initiated automatically. Exceptional payments may require manual handling. | E2E tests with a mock adapter in CI plus acceptance evidence from one authorised live payOS channel (Section 3.3). |
| No overselling, no duplicate tickets | Active reservations and issued tickets must not exceed event capacity; repeated verified payment callbacks must not issue duplicate tickets. | Concurrency and webhook-idempotency cases designed under WBS 4.3.2 and executed under WBS 6.1.1; technical spike under WBS 3.1.4. |
| Fast and reliable check-in | Preliminary target: at least 95% of scan requests return a valid / used / invalid result within 2 seconds under defined 4G test conditions. Invalid tickets and duplicate check-ins are rejected. Confirm measurement conditions in PA2. | System tests on real Android and iPhone devices. |
| Transparent approval | Every event shows its approval status, and every decision is kept in a history with the approver’s reason. | Acceptance tests for F02–F03. |
| Real-time visibility | The organiser dashboard reflects recorded ticket sales and check-ins within 5 seconds after server-side confirmation. | Integration and E2E tests for F08. |

Operating environment

- Client: any modern HTML5 browser (Chrome, Edge, Firefox, Safari – latest two versions) on desktop and mobile; the scanner needs a phone with a camera.

- Server: cloud hosting with HTTPS everywhere (also required by browsers for camera access).

- External services: payOS payment gateway (VietQR payment links and webhooks) and a transactional e-mail service.

The technology stack and the hardware and software environments are described in Sections 3.2 and 3.3.

Design and implementation constraints

- Process: waterfall model with V-model test planning; phase gates PA0–PA5 and a final presentation within 11 weeks; implementation in weeks 8–10 (Section 4.1).

- Team and budget: four students. PA0 set 8–10 h per member per week (about 12 h in W8–W10); on 21/10/2026 the team agreed to 12 h in W4–W5, 10 h in W6–W7, 13 h in W8 and 20 h in W9–W10 (Section 4.3). Only free tiers of hosting and tools are used.

- Technology: TypeScript for front end and back end, PostgreSQL database, REST API with a WebSocket channel for real-time updates (Section 3.2).

- Payments: UniEvent does not hold or aggregate funds. The PA5 delivery scope uses one authorised payOS payment channel with direct settlement to its account holder. Multi-organiser onboarding, per-organiser credential management and payment routing are excluded from PA5. F10 cancellation/refund policy automation remains optional; minimum handling of received-payment exceptions is required under F05–F06.

- Data protection: minimise collected personal data, apply role-based access controls, and avoid including personal data in QR ticket payloads. Data-handling requirements will be specified in PA2 with reference to applicable Vietnamese legislation, including Law No. 91/2025/QH15.

- Documentation: course templates for every PA, UML 2.5 for models, the C4 model for architecture, Architecture Decision Records for key decisions.

- Code quality target: ESLint/Prettier, Conventional Commits and reviewed PRs for repository changes. PA1 sections are co-edited in Google Docs and do not require separate PRs. A future pull_request application build/lint/test CI pipeline and required status checks remain to be configured.

Assumptions and dependencies

- Live-channel access remains an external dependency. Học coordinates the nominated account holder and TA approval; Minh verifies account eligibility, credentials and signed webhook access in the W4 technical spike (WBS 3.1.4), and Kiệt reviews the spike result. The mock adapter supports deterministic tests and a clearly labelled contingency demo; it does not establish completion of live integration. If authorisation/access is unavailable, Học obtains an explicit revised delivery decision from the TA rather than silently replacing the required channel with a mock.

- Prospective paid-ticket attendees are assumed to have access to a bank or payment app that supports VietQR; validate accessibility and offer free tickets without requiring such an app.

- The team plans to seek feedback from Student Volunteer Team organisers and Youth Union officers about event approval, refunds and conduct-score rules during PA2 (WBS 2.1.2); their availability and participation are not yet confirmed.

- The detailed problem statement, requirements and business rules will be specified in PA2. Essential open rules include: payment received after a reservation expires; whether an order is cancellable after payment; matching webhook order code, amount and status; safely retrying email without creating a second ticket; check-in/check-out state transitions; multi-role permissions; and the data-retention/access policy under Law No. 91/2025/QH15. Each rule needs an explicit acceptance test.

## Product Position Statement

| Element | Content |
| --- | --- |
| For | student clubs and Youth Union / Student Association officers at Vietnamese universities |
| Who | run events with Google Forms, manual bank-transfer reconciliation and paper attendance lists |
| The UniEvent | is a web-based event management and ticketing platform |
| That | integrates event approval, VietQR payment confirmation, signed QR ticket issuance and attendance tracking, with optional conduct-score evidence management |
| Unlike | disconnected workflows based on Google Forms, spreadsheets and manual bank transfers, or general-purpose event platforms such as Ticketbox and Luma |
| Our product | focuses on Vietnamese university workflows by integrating institutional event approval, free and low-cost ticketing, automated VietQR payment confirmation and verifiable attendance records in one platform |

User-specific position statements (derived from the overall statement; validated in PA2 interviews)

| Element | Attendee |
| --- | --- |
| For | students who attend campus events |
| Who | register through forms, pay by bank transfer and wait for a manual confirmation |
| The UniEvent | attendee portal |
| That | reserves a ticket, takes payment through VietQR and delivers a signed QR ticket automatically, then shows the attendance result |
| Unlike | Google Forms with manually confirmed transfers |
| Our product | issues exactly one verified ticket per paid order and keeps a visible attendance record (F05–F07) |

| Element | Club organiser |
| --- | --- |
| For | club organising committees |
| Who | run approval, registration, payment reconciliation and check-in with disconnected tools |
| The UniEvent | organiser workspace |
| That | covers event submission, ticket configuration, check-in staff assignment, automatic payment confirmation and a live dashboard |
| Unlike | spreadsheets and bank statements, or general platforms such as Ticketbox and Luma that have no institutional approval step |
| Our product | removes manual reconciliation in the normal case and shows sales and attendance live (F01–F06, F08) |

| Element | Check-in volunteer |
| --- | --- |
| For | volunteers at the venue entrance |
| Who | look attendees up in printed or shared lists |
| The UniEvent | mobile-browser scanner |
| That | validates signed QR tickets for the events they are assigned to |
| Unlike | list lookup or screenshots that can be reused |
| Our product | returns a valid, already-used or invalid result (target: 95% of scans within 2 seconds on 4G) and records check-in and check-out atomically (F07) |

| Element | Approver |
| --- | --- |
| For | Youth Union and Student Association officers |
| Who | receive event plans by e-mail or on paper |
| The UniEvent | approval queue |
| That | collects submissions from their unit and records approve, reject-with-reason and request-changes decisions |
| Unlike | e-mail threads and paper files |
| Our product | keeps every decision and reason in a searchable history, with optional bulk review of conduct-score evidence (F03, F09) |

| Element | System administrator |
| --- | --- |
| For | the operator responsible for UniEvent access |
| Who | must control which organisations exist and who holds organiser and approver rights |
| The UniEvent | administration console |
| That | manages organisations, scoped role grants, account status and the audit log |
| Unlike | informal sharing of form, spreadsheet and payment access |
| Our product | makes every privileged change and data export traceable to a named account (F01) |

## Stakeholders and Users

| # | Stakeholder / user | Description | Main interests |
| --- | --- | --- | --- |
| 1 | Academic stakeholder – instructor and TA | Teaching staff who supervise the project, review PA submissions and evaluate delivery against course requirements | A complete, consistent process; working software; fair individual contributions |
| 2 | End user – student (attendee) | Any student who joins events | Convenient ticket purchasing, access to issued tickets, accurate attendance records and optional conduct-score history if F09 is implemented |
| 3 | End user – club organiser | Member of a club’s organising committee | No manual reconciliation, real-time sales and attendance, easy approval process |
| 4 | Potential domain expert / pilot organisation – Student Volunteer Team | A student volunteer organisation known to the team lead; workflow validation and possible pilot participation are subject to the organisation's agreement | A workflow that fits real volunteer activities; reliable attendance records; a chance to pilot the system |
| 5 | End user – check-in volunteer | Club member working at the venue entrance | Fast and unambiguous scanning, works on their own phone |
| 6 | End user – Youth Union / Student Association officer | Approves events and (optionally) conduct score claims | Clear event information, decision history, reliable attendance evidence, bulk review |
| 7 | End user – system administrator | Operator who registers organisations, grants organiser and approver roles scoped to an organisation, and records the resolution of payment exceptions | A complete organisation register, secure scoped role assignments and traceable changes |
| 8 | External system – payOS | VietQR payment gateway used through the single authorised PA5 payment channel | Correct use of its API and webhook, secure handling of keys |
| 9 | External system – e-mail service | Transactional e-mail provider that delivers tickets and notifications | Correct use of its API, reliable delivery, secure handling of keys |
| 10 | Development team | Four students building UniEvent | Achievable scope, clear requirements, balanced workload, portfolio value |

User roles on the system (one account may hold several roles; organiser, approver and checker rights are scoped)

| Role | Who holds it | Granted by | What the role does in UniEvent | Features |
| --- | --- | --- | --- | --- |
| Guest | Any visitor without signing in | — | Browses published event pages | Public pages |
| Attendee | Any student with a verified university e-mail | Self-registration | Reserves and pays for tickets, holds QR tickets, views own attendance | F01, F05–F07; F09–F10 if built |
| Organiser | Member of a club organising committee | Administrator, for one organisation | Creates and submits events, configures ticket types, assigns check-in staff, monitors the dashboard, exports attendees | F01–F06, F08; F10 if built |
| Checker | Volunteer working at one event | Organiser, for one event | Scans tickets and records check-in and check-out | F07 |
| Approver | Youth Union / Student Association officer | Administrator, for one approving unit | Approves, rejects or requests changes to proposals from their unit; optional bulk review of conduct-score evidence | F03; F09 if built |
| Administrator | System operator appointed by the team for PA5 | Seeded at deployment; further admins by an existing admin | Manages organisations, role grants, account status, the audit log and payment-exception records | F01, F06 exceptions |

Actor × feature responsibility matrix (preliminary; authority is restricted by event/organisation scope)

C = create/change; V = authorised view; X = primary execution/use; — = no default permission. Organiser, checker and approver rights apply only within their assigned organisation, event or unit.

| Feature | Attendee | Organiser | Checker | Approver | Admin |
| --- | --- | --- | --- | --- | --- |
| F01 Account and sign-in | X own account | X own account | X own account | X own account | X own account; C lock/unlock accounts |
| F01 Organisations and role grants | — | C checker assignment for own events | — | — | C organisations; C organiser and approver grants; V audit log |
| F02 Event proposal | V published events | C draft, submit, revise | — | V proposals of own unit | V audit |
| F03 Event decision | V published status | V status and reasons | — | C approve / reject / request changes | V audit |
| F04 Ticket configuration | V offered ticket types | C ticket types and limits | — | V in proposal review | V audit |
| F05 Reserve / pay | C own reservation and payment | V orders of own events | — | — | V exception audit |
| F06 Issue ticket / exceptions | X receives ticket | V order status and exceptions of own events | — | — | C exception resolution record |
| F07 Check-in / check-out | X presents ticket | V attendance of own events | C check-in and check-out on assigned events | V attendance if F09 is used | V audit |
| F08 Dashboard / CSV | — | X dashboard; C CSV export | — | — | V operational audit |
| F09 Conduct-score evidence (Should) | V own records | V drafts of own events | — | C bulk review | V audit |
| F10 Cancellation / refund (Should) | C cancellation request | C refund decision under the policy | — | — | V audit |

Key data: source, stewardship and consumers (conceptual mapping, not a database schema)

| Data / future entity | Created by | Updated by | Used / exported by | PA2–PA3 decision |
| --- | --- | --- | --- | --- |
| Account | Student self-registration with a university e-mail | Account holder (profile); administrator (lock/unlock) | All signed-in roles | University e-mail policy and retention period. |
| Organisation (club, Youth Union or Student Association unit) | Administrator | Administrator (edit, deactivate) | Organisers and approvers within scope; attendees see the organiser name | Unit hierarchy and how a club proves its status. |
| Role grant | Administrator (organiser, approver); organiser (checker for own event) | The granting role revokes; an administrator may revoke any grant | Access checks on every request; audit log | Grant request flow, expiry and minimum audit fields. |
| Event / approval decision | Organiser (event form); approver (decision) | Organiser edits draft; approver changes decision status | Attendees view published events; organisers and officers audit | State transitions, change requests and ownership. |
| Ticket type / inventory | Organiser (price, sale window, cap, per-account limit) | Organiser before sale; system reserves and releases atomically | Attendees choose; organisers report | Transaction boundaries and overbooking constraints. |
| Reservation / payment status | Attendee reservation; verified payOS webhook | System only | Attendee receipt; organiser dashboard | Signature, amount, order code, expiry, idempotency. |
| Payment exception record | System flags a paid-but-unissued order | Administrator records the resolution; organiser confirms payer notification | Administrator, organiser of the event | Closure evidence and notification rules. |
| Ticket / attendance | System issues QR; checker scans | Server accepts valid state transitions atomically | Attendee proof; organiser CSV; optional officer review | Retention and check-in/check-out dispute procedure. |
| Audit log | System records grants, exports and exception resolutions | Append-only; nobody edits | Administrator | Retention under Law No. 91/2025/QH15. |

## Scope and Key Features

Features are prioritised using MoSCoW. Must-have features (F01–F08) define the required PA5 delivery scope. Should-have features (F09–F10) are conditional extensions and must not delay Must-have delivery. Could-have features (F11–F14) form a future backlog, excluded from the PA5 implementation baseline. Won't-have features (F15–F16) are outside the current project scope.

| ID | Feature | Primary actor(s) | Description | Priority (M/S/C/W) |
| --- | --- | --- | --- | --- |
| F01 | Accounts, organisations and role administration | All roles; Administrator; Organiser | Sign-up/sign-in with a university e-mail address; one account may hold several roles. Administrators register and deactivate organisations, grant and revoke organiser and approver roles scoped to an organisation, lock or unlock accounts and view the audit log. Organisers assign check-in staff to their own events. Guests browse published events without an account. | Must |
| F02 | Event creation and submission | Organiser | Organisers create an event (time, venue, capacity, poster, description) and submit it to their approving unit. | Must |
| F03 | Event approval workflow | Approver | Approvers approve, reject with a reason, or request changes; every decision is kept in an approval history. | Must |
| F04 | Ticket type configuration | Organiser | Price (0 VND for free tickets), quantity, sales window and per-account purchase limit for each ticket type. Audience restrictions are part of F11. | Must |
| F05 | Ticket reservation and VietQR payment | Attendee | A reservation holds tickets for 15 minutes. Paid tickets use the single authorised PA5 payOS channel; free tickets skip payment. Multi-organiser channel management is excluded. | Must |
| F06 | Payment confirmation and ticket issuing | System; Attendee; Administrator | Verifies the payOS callback signature, order, amount and status; processes callbacks idempotently; issues and e-mails one signed QR ticket. Paid-but-unissued orders are flagged and resolved by an administrator. | Must |
| F07 | QR check-in and check-out | Checker | Mobile-browser scanner validates signed tickets for assigned events, records check-in and check-out, and rejects invalid tickets, duplicate check-ins and duplicate check-outs. | Must |
| F08 | Real-time organiser dashboard | Organiser | Tickets sold, revenue and check-in rate updated in real time; CSV export of attendees. | Must |
| F09 | Conduct score records | Approver; Attendee | Optional: generates draft conduct-score evidence from check-in/check-out data with basic bulk review by authorised officers. Appeals and integration with official university systems are excluded from PA5. | Should |
| F10 | Cancellation and refund policy | Attendee; Organiser | Ticket cancellation and refund decisions under the refund policy; refunds are recorded, money is returned manually. | Should |
| F11 | Discount codes and special tickets | Organiser; Attendee | Early-bird tickets, club-member-only tickets (requires an organiser-maintained member list) and conditional discount codes. | Could |
| F12 | Waitlist | Attendee; Organiser | Students join a waitlist for sold-out ticket types and are invited in order when tickets are released. | Could |
| F13 | Offline check-in | Checker | Progressive web app mode that checks tickets without network access and synchronises later. | Could |
| F14 | AI writing assistant for organisers | Organiser | Suggests event descriptions and summarises post-event feedback; the organiser approves every suggestion. | Could |
| F15 | Seat maps and reserved seating | Attendee | Choosing a specific seat when buying a ticket. | Won’t |
| F16 | Native mobile applications | All roles | iOS/Android apps; UniEvent stays a responsive web app. | Won’t |

Shaded rows are Must-have features.

PA5 payment delivery and exception handling

The required delivery is one authorised live payOS payment channel supporting F05–F06: reservation, payment-link creation, signed callback verification, order/amount/status matching, idempotent ticket issuance and ticket delivery. Free tickets bypass payment. CI uses the mock adapter; acceptance includes evidence from the authorised live channel. The account holder and permission to test remain to be confirmed by Học with the TA by W4 Thursday, before real transfers.

If a received payment cannot produce a valid ticket, UniEvent retains transaction evidence, flags the exception for authorised review and prevents duplicate processing. Kiệt coordinates technical investigation; Học contacts the organiser/account holder. The account holder handles payer communication and any manual return of funds outside UniEvent. Resolution and payer-notification evidence are recorded before closure. This minimum workflow is required even when optional F10 is deferred; no automated refund or custody of funds is promised.

Out of scope:

- Holding or aggregating organisers’ funds, distributing payouts, and onboarding or routing payments across multiple organiser-owned payment channels are outside PA5. The delivery baseline contains one authorised payOS channel.

- International card payments and currencies other than VND.

- Native iOS/Android applications – UniEvent is a responsive web application only.

- Direct integration with the university’s official conduct score or student-information systems (UniEvent exports records instead).

- Seat maps and reserved seating.

Changes since PA0

PA0 is the baseline for this document. PA1 retains F01–F10 priority categories while clarifying QR check-in/check-out rules and the optional scope of conduct-score features. F11–F14 are recorded as Could-have backlog; F15–F16 are Won't-have. Other material changes are listed below.

| Item | PA0 | PA1 | Section | Changed by |
| --- | --- | --- | --- | --- |
| Feature list | F01–F10 (eight Must, two Should) | F11–F14 added as Could-have backlog; F15–F16 recorded as Won't-have. F01–F10 keep their PA0 priority categories. | 2.4 | Thái Quang Huy |
| F01 administration | Administrators “manage clubs, accounts, roles and system-wide policies” | Administrators manage organisations, organiser/approver grants scoped to an organisation, account status and the audit log; organisers assign check-in staff to their own events (new WBS 5.2.13). | 2.3, 2.4 | Thái Quang Huy |
| F04 Ticket types | Price, quantity, sales window, per-person limit | Per-account purchase limit; audience restrictions such as club-member-only tickets moved to F11. | 2.4 | Thái Quang Huy |
| F07 Attendance | QR check-in; reject invalid/used tickets | Separate check-in and check-out with valid state transitions and duplicate-scan rejection. | 2.4 | Thái Quang Huy |
| F09 Conduct score | Records and bulk review | Remains Should-have; basic draft evidence records and bulk review only; appeals and official-system integration excluded from PA5. | 2.4 | Thái Quang Huy |
| Stakeholders and users | Five target-user groups | Ten stakeholders and six system roles, including Guest, the instructor/TA, the pilot organisation and external systems. | 2.3 | Thái Quang Huy |
| Payment scope | Payments go to each organiser's own payOS account | One authorised live payOS channel for PA5; multi-organiser onboarding and routing excluded. | 2.4 | Lê Nguyễn Quốc Học |
| Payment test environment | Mock adapter mentioned as a risk mitigation | Mock adapter for CI and labelled contingency demo; live acceptance evidence from the authorised channel. | 3.3 | Lê Nguyễn Quốc Học |
| Technology | “Not final – confirmed in PA1” | Selected: Next.js, NestJS, PostgreSQL/Prisma; reasons in Section 3.2. Versions and hosting providers confirmed during setup. | 3.2 | Trần Vũ Anh Kiệt |
| Effort estimate | About 43 h for Must-have implementation, plus tests/review | 94 h for WBS 5.2; 120 h including foundation and unit-test/CI work; 427 h for the required project. | 4.3 | Lê Nguyễn Quốc Học |
| Capacity | 8–10 h/member/week; about 12 h in W8–W10 | Raised by all-member agreement on 21/10/2026: 12 h in W4–W5, 13 h in W8, 20 h in W9–W10; demand is covered with 8 h slack in each window (Section 4.3). | 4.3–4.5 | Lê Nguyễn Quốc Học |

# Proposed Solution

## Preliminary Architecture

UniEvent is used by five authenticated roles – attendee, organiser, checker, approver and administrator – and by unauthenticated guests who browse published events; it depends on two external systems: payOS, whose API issues VietQR payment links and notifies UniEvent of completed payments through webhooks, and an e-mail service, which delivers tickets and notifications

Figure 1. C4 System Context diagram of UniEvent

## Technology Stack

| Layer | Technology | Reason for choice |
| --- | --- | --- |
| Front end | Next.js (React, TypeScript), Tailwind CSS | Responsive pages and server-side rendering; large ecosystem; TypeScript types shared with the back end |
| Back end | NestJS on Node.js LTS (TypeScript), REST + WebSocket (Socket.IO) | Module structure matches our feature modules; dependency injection makes unit testing easy; built-in WebSocket gateway for the real-time dashboard |
| Database | PostgreSQL with Prisma ORM | ACID transactions and row-level locks prevent overselling; relational model fits events, tickets and orders; versioned migrations |
| Payment and e-mail | payOS (VietQR) behind a PaymentProvider interface with a mock adapter; transactional e-mail service (e.g., Resend) | VietQR is the payment method students already use; the mock adapter keeps CI and demos independent of the real gateway |
| Hosting / deployment | Docker; Vercel (web), Render or Railway (API), Neon (PostgreSQL) | Candidate providers; verify quotas, supported connections and HTTPS before choosing the deployment configuration. |
| Testing & CI | Jest, Supertest, Playwright, k6, GitHub Actions, ESLint, SonarQube Cloud | Covers unit, integration, end-to-end and load testing; CI runs on every pull request; static analysis as a quality gate |

The PA1 technology choices in Section 3.2 are selected for this project. Exact library versions are pinned at implementation setup; upgrades require compatibility checks. Hosting and e-mail providers remain deployment choices to be verified against quotas, WebSocket support and the approved budget.

## Hardware and Operating Environment

| Environment | Hardware / software |
| --- | --- |
| Development | Members' laptops (Windows, macOS or Linux, 8 GB RAM or more) Node.js LTS, Docker Desktop, Git, VS Code with ESLint/Prettier, Figma, draw.io / PlantUML |
| Testing | Desktop browsers: Chrome, Edge, Firefox (latest) At least one Android phone (Chrome) and one iPhone (Safari) for QR scanning and responsive tests 4G connection for check-in performance tests; GitHub Actions runners for automated tests |
| Staging / production | Web app, API container and PostgreSQL on providers selected against deployment requirements and available quotas. One nominated, authorised payOS channel is required for live acceptance testing; account-holder and TA permission must be recorded before real transfers. |
| End users | Any device with a modern HTML5 browser; a camera for the check-in scanner; a banking app for VietQR payments |

# Project Plan

## Process and Phase Gates

The project follows the waterfall model. Each phase ends with a phase gate (a PA submission). After a PA is submitted it becomes a baseline; later changes must be updated in the document and listed in the next PA.

Course weeks map to calendar dates as follows; W1 starts on Monday 5 October 2026. A deadline published on Moodle overrides the planned week-end marker, and each internal freeze moves with it (drafts at T−2 days, reviewed freeze at T−1 day).

| Week | Dates (2026) | Gate or fixed date |
| --- | --- | --- |
| W1 | 05/10 – 11/10 | — |
| W2 | 12/10 – 18/10 | PA0 submitted Wed 14/10, 22:00 |
| W3 | 19/10 – 25/10 | PA1 due Wed 21/10, 22:00 |
| W4 | 26/10 – 01/11 | — |
| W5 | 02/11 – 08/11 | PA2 |
| W6 | 09/11 – 15/11 | — |
| W7 | 16/11 – 22/11 | PA3 |
| W8 | 23/11 – 29/11 | PA4 |
| W9 | 30/11 – 06/12 | — |
| W10 | 07/12 – 13/12 | PA5 |
| W11 | 14/12 – 20/12 | Final presentation and demo |

| PA | Phase | Due | Exit criteria |
| --- | --- | --- | --- |
| PA1 | Initiation & planning | Wed 21/10/2026, 22:00 (Moodle) | Vision, scope, WBS, estimates, schedule and risk register reviewed by all members; repository, board and Discord set up; PDF and source submitted and committed to /pa/PA1 |
| PA2 | Requirements | End of week 5 | Every Must-have FR numbered with acceptance criteria; measurable NFRs; business rules; all Must-have use cases specified; mockups for main use cases; traceability F to FR to UC complete; review record with all issues closed |
| PA3 | Design | End of week 7 | C4 context and container, component and deployment diagrams completed; at least 3 ADRs; consistent class, sequence and state diagrams; normalized database schema with ERD, table specifications and indexes; screen flow and accessibility checklist; all Must-have FRs traced to design elements; design consistency reviewed. |
| PA4 | Test planning | End of week 8 | Test plan completed with scope, levels, types, environment, entry/exit criteria and defect management; EP, BVA and decision tables applied; test cases documented with preconditions, test data, steps and expected results; every Must-have FR covered by at least one test case. |
| PA5 | Implementation, testing & deployment | End of week 10 | All Must-have features implemented and test cases executed with results recorded; no open critical or major defects; unit-test coverage reported; at least 2 use cases × 2 scenarios automated in CI; code reviewed through PRs and static analysis completed; application deployed with demo video; retrospective completed. |
| Final | Presentation & demo | Week 11 | Slides cover all required content and are rehearsed with a timer; every member speaks at least 2 minutes in English; key scenarios demonstrated live with a backup video available. |

## Work Breakdown Structure (WBS)

The deliverable-oriented WBS contains Level 0 (UniEvent project), seven Level-1 workstreams, 26 Level-2 deliverables and 72 Level-3 work packages. Figure 2 shows Levels 0–2; Table 1 maps each deliverable to its Level-3 IDs. Section 4.3 lists every work package with its owner, week, estimate and output. Each Level-3 work package is executed by exactly one owner; a different member reviews it, and the reviewer is recorded on the GitHub issue.

Work packages will be tracked on GitHub Projects with the same WBS ID, owner, estimate, due date, evidence, and status. Monitoring (1.3) is recurring from W2 to W10. Work package 3.1.4 is an exploratory payment/concurrency technical spike scheduled in W4 to reduce feasibility uncertainty; the remaining architecture design activities (3.1.1–3.1.3) are scheduled in W6–W7 after the PA2 gate. The W4 spike does not constitute approval of the PA3 design baseline. Should-have features (F09/F10) remain conditional and are excluded from the committed PA5 delivery baseline.

Figure 2. WBS of UniEvent (levels 1-2)

Table 1. Deliverables (level 2) and their work packages (level 3)

| WBS ID | Phase / deliverable | Work packages | Owners / phase gate |
| --- | --- | --- | --- |
| 1 | Project management |  |  |
| 1.1 | Initiation (PA0) | 1.1.1–1.1.2 (2) | A, B / PA0 |
| 1.2 | Planning (PA1) | 1.2.1–1.2.5 (5) | A, B, C, D / PA1 |
| 1.3 | Monitoring and control | 1.3.1–1.3.3 (3) | A, B / PA5 |
| 1.4 | Tools and collaboration setup | 1.4.1–1.4.3 (3) | B / PA1 |
| 2 | Requirements (PA2) |  |  |
| 2.1 | Requirements elicitation | 2.1.1–2.1.2 (2) | B / PA2 |
| 2.2 | Requirements specification | 2.2.1–2.2.8 (8) | A, B, C, D / PA2 |
| 2.3 | Prototype | 2.3.1 (1) | C / PA2 |
| 2.4 | Requirements validation | 2.4.1–2.4.2 (2) | B, C / PA2 |
| 3 | Design (PA3) |  |  |
| 3.1 | Architecture design | 3.1.1–3.1.4 (4) | C, D / PA3 |
| 3.2 | Object-oriented design | 3.2.1–3.2.3 (3) | A, B / PA3 |
| 3.3 | Data design | 3.3.1–3.3.2 (2) | D / PA3 |
| 3.4 | UI/UX design | 3.4.1 (1) | C / PA3 |
| 3.5 | Design consistency | 3.5.1 (1) | A / PA3 |
| 4 | Test planning (PA4) |  |  |
| 4.1 | Test plan | 4.1.1 (1) | D / PA4 |
| 4.2 | Test design | 4.2.1–4.2.2 (2) | A, B / PA4 |
| 4.3 | Test cases | 4.3.1–4.3.3 (3) | A, C, D / PA4 |
| 4.4 | Test traceability | 4.4.1 (1) | B / PA4 |
| 5 | Implementation (PA5) |  |  |
| 5.1 | Foundation | 5.1.1–5.1.2 (2) | B, C / PA5 |
| 5.2 | Must-have features | 5.2.1–5.2.13 (13) | A, B, C, D / PA5 |
| 5.3 | Should-have features | 5.3.1–5.3.2 (2) | B, D / PA5 |
| 5.4 | Unit testing and code review | 5.4.1–5.4.2 (2) | C, D / PA5 |
| 6 | Testing and deployment (PA5) |  |  |
| 6.1 | Test execution | 6.1.1–6.1.3 (3) | B, D / PA5 |
| 6.2 | Deployment | 6.2.1–6.2.2 (2) | A, D / PA5 |
| 6.3 | Code quality | 6.3.1 (1) | A / PA5 |
| 7 | Closing (Final) |  |  |
| 7.1 | Retrospective | 7.1.1 (1) | A / PA5 |
| 7.2 | Presentation and demo | 7.2.1–7.2.2 (2) | A, C / Final |

## Estimation

Effort is estimated in person-hours (one person working for one hour), not elapsed calendar time. Each estimate covers the owner’s work to produce the stated output, including addressing review comments. The team reviewed these estimates at the PA1 freeze; actual hours will be logged on each GitHub issue and compared in WBS 7.1.1. Work packages are generally scoped to approximately 3–9 person-hours; actual work exceeding the estimate must be re-estimated or split.

Three estimation methods are used: EJ = expert judgement (the assigned team member assesses the steps and complexity); AN = analogy (reference to comparable tasks or reusable templates/components); and 3P = three-point estimation, with optimistic O, most-likely M, and pessimistic P hours. For 3P packages, the weighted estimate is (O + 4M + P) / 6. For example, the payment-webhook technical spike uses 4/8/12 hours, yielding 8 hours.

The estimates assume a responsive web application, an existing GitHub/Discord setup, reusable web libraries, payOS sandbox access, a transactional email provider, and no native mobile app or official university information-system integration. They are sensitive to external-service constraints, especially payOS webhooks and concurrency, and must be revisited after the week-4 spike. Estimates for optional F09 and F10 are shown separately and excluded from the required PA5 effort.

Table 2. Work packages (level 3) with owners, weeks, estimates and outputs

| WBS ID | Work package | Owner | Week(s) | Effort (h) | Method / assumptions | Output (done when) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Project Management |  |  | 74 | Phase subtotal |  |
| 1.1.1 | Finalize project idea and feasibility assessment | A | W1–W2 | 5 | EJ; PA0 idea and competitor scan | Project idea section of T07-PA0 approved for PA0 submission |
| 1.1.2 | Finalize team contract and responsibilities | B | W1–W2 | 4 | EJ; four-member contract review | Signed team contract in T07-PA0 |
| 1.2.1 | Define project vision, scope and stakeholders | B | W2–W3 | 6 | EJ; reuse approved PA0 scope | PA1 Section 2 reviewed by Học |
| 1.2.2 | Prepare preliminary architecture and technology choices | C | W2–W3 | 6 | EJ; preliminary C4 and stack only | PA1 Section 3 with Figure 1, reviewed by Minh |
| 1.2.3 | Create WBS and effort estimation | A | W2–W3 | 8 | EJ; 72 WPs and cross-check | PA1 Sections 4.2–4.3 with Figure 2, reviewed by Kiệt |
| 1.2.4 | Prepare schedule, roles and cost estimate | A | W2–W3 | 8 | EJ; Gantt and cost workbook | PA1 Sections 4.4–4.6 with Figure 3, reviewed by Kiệt |
| 1.2.5 | Prepare risk register and tools & collaboration section | D | W2–W3 | 6 | EJ; at least five scored risks | PA1 Sections 5–6, reviewed by Huy |
| 1.3.1 | Prepare weekly status reports and meeting records | A | W2–W10 | 9 | AN; nine weekly reports and minutes | W2–W10 status reports in /docs/management/weekly by Sunday 22:00 |
| 1.3.2 | Monitor task-board progress and commitments | A | W2–W10 | 7 | AN; weekly board checks | Board reviewed weekly; overdue items listed in the weekly report |
| 1.3.3 | Track risks, issues and approved changes | B | W2–W10 | 6 | EJ; risks and changes logged weekly | Risk and change log updated in each weekly report |
| 1.4.1 | Configure Git repository and branch protection | B | W2 | 4 | AN; existing GitHub repository | Repository structure and active “Protect main” ruleset |
| 1.4.2 | Set up GitHub Projects task board | B | W2 | 3 | AN; one GitHub Projects board | “Team Management” board with issues, labels and status options |
| 1.4.3 | Set up team communication channel | B | W2 | 2 | AN; existing Discord server | Discord server with issue notifications configured |
| 2 | Requirements (PA2) |  |  | 75 | Phase subtotal |  |
| 2.1.1 | Collect stakeholder needs and pain points | B | W4 | 6 | EJ; short stakeholder interviews | Interview notes in /docs/requirements |
| 2.1.2 | Validate event workflows and project assumptions | B | W4–W5 | 5 | EJ; validate with other organisers | Validated assumption list with sources |
| 2.2.1 | Specify numbered FRs and acceptance criteria for F01–F03 | A | W4–W5 | 6 | AN; three features, shared template | Numbered FRs with acceptance criteria for F01–F03 |
| 2.2.2 | Specify numbered FRs and acceptance criteria for F04–F06 | A | W4–W5 | 7 | AN; three ticket/payment features | Numbered FRs with acceptance criteria for F04–F06 |
| 2.2.3 | Specify numbered FRs and acceptance criteria for F07–F08 | C | W4–W5 | 6 | AN; two check-in/dashboard features | Numbered FRs with acceptance criteria for F07–F08 |
| 2.2.4 | Specify measurable NFRs and business rules | D | W4–W5 | 7 | EJ; measurable targets and rules | NFR list with targets and business-rule table |
| 2.2.5 | Develop use-case model and actor relationships | B | W4–W5 | 5 | AN; actors and UML relationships | UML use-case diagram with actor generalisation |
| 2.2.6 | Specify account, administration, event and approval use cases | D | W5 | 7 | AN; concise numbered UC flows | UC specifications for F01–F03, including administrator use cases |
| 2.2.7 | Specify ticketing and payment use cases | A | W5 | 5 | EJ; multiple payment-related UC flows | UC specifications for F04–F06 |
| 2.2.8 | Specify check-in and dashboard use cases | C | W4–W5 | 4 | AN; split from former 2.2.7 | UC specifications for F07–F08 |
| 2.3.1 | Create mockups for main use cases | C | W4–W5 | 8 | AN; low-fidelity key-use-case mockups | Mockups for every main use case, linked to UC IDs |
| 2.4.1 | Build feature–FR–UC traceability matrix | C | W5 | 4 | AN; F–FR–UC links in matrix | Traceability matrix F → FR → UC |
| 2.4.2 | Conduct requirements review and resolve blocking issues | B | W5 | 5 | EJ; one review + issue resolution | Review record with all blocking issues closed |
| 3 | Design (PA3) |  |  | 68 | Phase subtotal |  |
| 3.1.1 | Create C4 context and container diagrams | C | W6 | 5 | AN; C4 context/container templates | C4 context and container diagrams |
| 3.1.2 | Create component and deployment diagrams | C | W6–W7 | 6 | EJ; component/deployment scope | Component and deployment diagrams |
| 3.1.3 | Document at least three architecture decision records (ADRs) | D | W6–W7 | 6 | AN; three concise ADRs | At least three ADRs in /docs/design |
| 3.1.4 | Run payment-webhook and concurrent-reservation technical spike | D | W4 | 8 | 3P (4/8/12); authorised channel and two technical risks | Spike report: payOS channel access, webhook signature, idempotency and concurrency results |
| 3.2.1 | Prepare class diagrams and class specifications | B | W6–W7 | 7 | EJ; domain classes from UCs, with specs | Class diagram and class specifications traced to UCs |
| 3.2.2 | Prepare key sequence diagrams | A | W6–W7 | 6 | AN; two to three key scenarios | Two to three sequence diagrams |
| 3.2.3 | Prepare key state diagrams | B | W6–W7 | 5 | AN; ticket/order/event states | State diagrams for ticket, order and event |
| 3.3.1 | Create ERD and database table specifications | D | W6–W7 | 8 | EJ; core entities and table specs | ERD and table specifications |
| 3.3.2 | Review normalization, constraints and indexes | D | W7 | 5 | EJ; review keys/index trade-offs | Normalisation, constraint and index notes |
| 3.4.1 | Define screen flow, key screens and accessibility checklist | C | W6–W7 | 7 | AN; reuse PA2 mockups | Screen flow, key screens and accessibility checklist |
| 3.5.1 | Review design consistency and FR-to-design traceability | A | W7 | 5 | EJ; all Must-have FR links | Consistency review record; every Must-have FR traced to design |
| 4 | Test Planning (PA4) |  |  | 36 | Phase subtotal |  |
| 4.1.1 | Define test scope, levels, types, environment, entry/exit criteria and defect workflow | D | W8 | 6 | EJ; complete test-plan template | Test plan document |
| 4.2.1 | Design equivalence-partitioning (EP) and boundary-value (BVA) scenarios | A | W8 | 4 | AN; selected boundaries/partitions | EP and BVA tables |
| 4.2.2 | Design decision-table scenarios for business rules | B | W8 | 4 | AN; key conditional business rules | Decision tables for key business rules |
| 4.3.1 | Write account and event-approval test cases | A | W8 | 5 | AN; reusable test-case template | Test cases for F01–F03 |
| 4.3.2 | Write ticketing and payment test cases | D | W8 | 7 | EJ; payment negative-path coverage | Test cases for F04–F06, including negative paths |
| 4.3.3 | Write QR check-in and dashboard test cases | C | W8 | 6 | AN; QR/dashboard test coverage | Test cases for F07–F08 |
| 4.4.1 | Build and review FR-to-test-case coverage matrix | B | W8 | 4 | AN; test cases linked to all Must FRs | Coverage matrix: every Must-have FR has at least one test case |
| 5 | Implementation (PA5) |  |  | 136 | Phase subtotal |  |
| 5.1.1 | Set up application skeleton and database foundation | C | W8 | 6 | EJ; established web stack; seed DB | Running Next.js/NestJS skeleton with migrations and seed data |
| 5.1.2 | Set up initial CI and shared configuration | B | W8 | 4 | AN; basic PR build/test workflow | PR build/lint/test workflow set as a required status check |
| 5.2.1 | Implement university-email authentication and role-based access (F01) | B | W9 | 8 | EJ; library auth; no campus SSO | Merged PR: sign-up/sign-in and role checks with unit tests |
| 5.2.2 | Implement event creation and submission (F02) | A | W9 | 6 | AN; ordinary event CRUD/forms | Merged PR: event form and submission with unit tests |
| 5.2.3 | Implement event approval and decision history (F03) | A | W9 | 7 | AN; status workflow and history | Merged PR: approval queue and decision history with unit tests |
| 5.2.4 | Implement ticket types, inventory and sales-window rules (F04) | C | W9 | 6 | AN; core ticket CRUD/constraints | Merged PR: ticket-type rules with unit tests |
| 5.2.5 | Implement ticket reservation, concurrency safeguards and 15-minute expiry (F05) | C | W9 | 9 | 3P (5/9/13); reuse tested DB transactions | Merged PR: reservation, hold and expiry with concurrency tests |
| 5.2.6 | Integrate payOS checkout and VietQR payment initiation (F05) | D | W9 | 8 | 3P (4/8/12); authorised payOS channel and mock fixtures | Merged PR: payment-link creation through the PaymentProvider interface |
| 5.2.7 | Implement verified payment webhooks and duplicate-event handling (F06) | D | W9 | 9 | 3P (5/9/13); webhook/idempotency | Merged PR: signed, idempotent webhook handling with tests |
| 5.2.8 | Implement QR ticket issuing and email delivery (F06) | A | W9–W10 | 8 | EJ; mail provider and QR lib | Merged PR: one signed QR ticket per paid order, e-mailed |
| 5.2.9 | Implement mobile-browser QR scanning interface (F07) | C | W9–W10 | 7 | AN; mobile camera/QR library | Merged PR: scanner page working on Android and iPhone |
| 5.2.10 | Implement atomic QR check-in and validated check-out (F07) | C | W10 | 9 | 3P (5/9/13); atomic check-in, stateful check-out | Merged PR: check-in/check-out state transitions with repeated-scan tests |
| 5.2.11 | Implement real-time organiser dashboard (F08) | B | W9–W10 | 8 | EJ; lightweight live updates only | Merged PR: live dashboard over WebSocket |
| 5.2.12 | Implement attendee-list and statistics CSV export (F08) | B | W10 | 4 | AN; simple CSV export | Merged PR: CSV export limited to authorised organisers |
| 5.2.13 | Implement organisation management and scoped role assignment (F01) | B | W9 | 5 | AN; reuses 5.2.1 guards and 5.2.2 form components | Merged PR: admin organisation CRUD, organiser/approver grants, checker assignment, audit entries |
| 5.3.1 | Implement optional attendance/conduct-score records (F09) | B | Conditional | 7 | EJ; optional basic records only | Only if R8 allows: draft evidence records and bulk review |
| 5.3.2 | Implement optional ticket cancellation and refund handling (F10) | D | Conditional | 9 | EJ; optional policy workflow only | Only if R8 allows: cancellation requests and recorded refunds |
| 5.4.1 | Consolidate module unit tests and coverage report | C | W10 | 8 | EJ; tests are written inside each feature WP | Coverage report and list of untested modules |
| 5.4.2 | Automate two use cases × two scenarios and PR checks in CI | D | W10 | 8 | EJ; 2 UCs × 2 scenarios in CI | Four automated E2E scenarios running on every PR |
| 6 | Testing and Deployment (PA5) |  |  | 36 | Phase subtotal |  |
| 6.1.1 | Execute Must-have test cases and record results | D | W10 | 8 | EJ; run all Must-have test cases | Executed test cases with pass/fail results |
| 6.1.2 | Record defects, verify fixes and run regression tests | B | W10 | 7 | EJ; one fix/regression cycle | Defect log and regression results |
| 6.1.3 | Prepare test-exit and defect summary report | B | W10 | 5 | AN; results and exit template | Test report against the exit criteria |
| 6.2.1 | Deploy application and verify environment configuration | D | W9–W10 | 7 | EJ; free-tier hosting where viable | Deployed staging/production URL with verified secrets and HTTPS |
| 6.2.2 | Run deployment smoke tests and record demo video | A | W10 | 4 | EJ; end-to-end smoke/video | Smoke-test record and demo video |
| 6.3.1 | Run static analysis and final code-quality review | A | W10 | 5 | AN; ESLint/static check/report | Static-analysis report with critical findings closed |
| 7 | Closing (PA5–Final) |  |  | 18 | Phase subtotal |  |
| 7.1.1 | Prepare retrospective and plan-versus-actual analysis | A | W10 | 5 | EJ; plan-vs-actual and AI lessons | Retrospective with plan-versus-actual hours |
| 7.2.1 | Prepare final presentation slides | A | W11 | 7 | AN; standard final slide deck | Final slide deck |
| 7.2.2 | Prepare demo scenario and coordinate timed rehearsal | C | W11 | 6 | EJ; 4 speakers, timed rehearsal | Demo script and timed rehearsal record |

Table 3. Estimated effort summary

| WBS group | Effort | Notes |
| --- | --- | --- |
| 1. Project Management | 74 | Continuous tasks across weeks 2–10 |
| 2. Requirements (PA2) | 75 |  |
| 3. Design (PA3) | 68 |  |
| 4. Test Planning (PA4) | 36 |  |
| 5. Implementation (PA5) | 136 | Includes optional F09/F10: 16 h |
| 6. Testing and Deployment (PA5) | 36 |  |
| 7. Closing (PA5–Final) | 18 | PA5 retrospective and Final |
| TOTAL INCLUDING OPTIONAL | 443 | Required scope: 427 |

Scope totals. Total including optional F09/F10 = 443 person-hours; required scope excluding F09/F10 (16 h) = 427 person-hours.

Responsibility versus effort. Owner totals including optional work are A = 117 h, B = 114 h, C = 103 h, D = 109 h; for the required scope they are A = 117 h, B = 107 h, C = 103 h, D = 100 h. Each total is the planned execution time of that member, because every work package has a single executing owner. Actual hours are logged on GitHub issues.

Effort reconciliation. Table 2 contains 72 work packages totalling 443 person-hours with F09/F10 included. The required-scope figure is 427 person-hours after excluding optional WBS 5.3.1 (7 h) and 5.3.2 (9 h). WBS 2.2 sums to 47 h and WBS 5.2 sums to 94 h. These are effort figures, not durations; Table 2 is the source of truth for every later total.

Capacity reconciliation. W8–W10 require 204 person-hours: 36 h for PA4, 120 h for required implementation and unit-test/CI work, 36 h for testing/deployment, 5 h for the retrospective and 7 h for monitoring. The availability agreed on 21/10/2026 provides 4 × 13 + 4 × 20 × 2 = 212 h in W8–W10, leaving 8 h of slack, and 4 × 12 × 2 = 96 h in W4–W5 for 88 h of demand. Optional F09–F10 are excluded from both figures.

Feasibility and scheduling notes

Availability baseline. PA0 set 8–10 h per member per week, rising to about 12 h in W8–W10. On 21/10/2026 all four members agreed to 12 h in W4–W5, 10 h in W6–W7, 13 h in W8, 20 h in W9–W10 and 8 h in W11. Estimates were not reduced to fit the hours; unused earlier time is not treated as available for later work.

| Window | Agreed capacity | Allocated estimated effort | Capacity minus demand |
| --- | --- | --- | --- |
| W1–W3 | 10 h × 4 × 3 = 120 | 52 initiation/planning/tools + 5 monitoring = 57 | +63 |
| W4–W5 | 12 h × 4 × 2 = 96 | 75 requirements + 8 exploratory spike + 5 monitoring = 88 | +8 |
| W6–W7 | 10 h × 4 × 2 = 80 | 60 design (excluding W4 spike) + 5 monitoring = 65 | +15 |
| W8–W10 | 13 h × 4 + 20 h × 4 × 2 = 212 | 36 PA4 + 161 required PA5 + 7 monitoring = 204 | +8 |
| W11 | 8 h × 4 × 1 = 32 | 13 presentation and demo = 13 | +19 |

## Schedule

Figure 3. Target Gantt chart with actual PA0/PA1 deadlines and planned phase gates

Scheduling convention. W denotes the course week; weekdays form a relative Monday–Sunday planning calendar. FS/SS/FF mean finish-to-start, start-to-start and finish-to-finish; lags are calendar days. This relative schedule must be mapped to the actual Moodle deadline for every PA before baselining. Individual drafts finish at T−2 days, integration/review corrections and freeze occur at T−1, and submission occurs at T. Saturday validation/release rows represent integration checks.

Table 4. Target schedule and dependencies (*calendar CPM only)

| ID | Activity | Start | Finish | Predecessors | CPM critical* |
| --- | --- | --- | --- | --- | --- |
| 1.1 | Initiation / PA0 | W1 Mon 05/10 | W2 Wed 14/10 | — | Yes |
| 1.4 | Tools setup | W2 Mon 12/10 | W2 Wed 14/10 | 1.1 SS+7d | No |
| 1.3 | Monitoring | W2 Mon 12/10 | W10 Sun 13/12 | 1.1 SS+7d | No |
| 1.2 | Planning / PA1 | W2 Sat 17/10 | W3 Wed 21/10 | 1.1 FS+2d; 1.4 FS | Yes |
| 2.1 | Requirements elicitation | W4 Mon 26/10 | W5 Mon 02/11 | 1.2 FS+4d | Yes |
| 3.1.4 | Payment/concurrency spike | W4 Tue 27/10 | W4 Fri 30/10 | 2.1 SS+1d; exploratory only | No |
| 2.2 | Requirements specification | W4 Thu 29/10 | W5 Fri 06/11 | 2.1 SS+3d | Yes |
| 2.3 | Prototype / mockups | W4 Sun 01/11 | W5 Fri 06/11 | 2.1 SS+6d | Yes |
| 2.4 | Requirements validation | W5 Wed 04/11 | W5 Sat 07/11 | 2.2 SS+6d; 2.3 SS+3d; both FF+1d; 3.1.4 FS | Yes |
| 3.1 | Architecture (excl. spike) | W6 Mon 09/11 | W7 Mon 16/11 | 2.4 FS+1d | Yes |
| 3.3 | Data design | W6 Thu 12/11 | W7 Thu 19/11 | 3.1 SS+3d | No |
| 3.4 | UI/UX design | W6 Thu 12/11 | W7 Thu 19/11 | 3.1 SS+3d | No |
| 3.2 | OO design | W6 Sun 15/11 | W7 Fri 20/11 | 3.1 SS+6d; 3.1 FF+4d | Yes |
| 3.5 | Design consistency | W7 Sat 21/11 | W7 Sat 21/11 | 3.2 FS; 3.3 FS; 3.4 FS | Yes |
| 4.1 | Test plan | W8 Mon 23/11 | W8 Wed 25/11 | 3.5 FS+1d | Yes |
| 4.2 | Test design | W8 Mon 23/11 | W8 Wed 25/11 | 3.5 FS+1d | Yes |
| 4.3 | Test cases | W8 Wed 25/11 | W8 Fri 27/11 | 4.1 SS+2d; 4.2 SS+2d; both FF+2d | Yes |
| 5.1 | Foundation / initial CI | W8 Fri 27/11 | W8 Sun 29/11 | 3.5 FS+5d; foundation only, no feature delivery | Yes |
| 4.4 | Test traceability | W8 Sat 28/11 | W8 Sat 28/11 | 4.3 FS | Yes |
| 5.2 | Must-have implementation | W9 Mon 30/11 | W10 Wed 09/12 | 4.4 FS+1d; 5.1 FS | Yes |
| 5.4 | Unit-test / CI work | W9 Mon 30/11 | W10 Fri 11/12 | 5.1 FS; 5.2 FF+2d | Yes |
| 6.3 | Code-quality work | W9 Mon 30/11 | W10 Fri 11/12 | 5.1 FS; 5.2 FF+2d | Yes |
| 6.2 | Deployment preparation + release | W9 Mon 30/11 | W10 Sat 12/12 | 5.1 FS; 6.1 FF+1d; 5.4 FF+1d; 6.3 FF+1d | Yes |
| 6.1 | Test execution / E2E | W10 Thu 10/12 | W10 Fri 11/12 | 5.2 FS; 5.4 FF; 6.3 FF | Yes |
| 7.1 | Retrospective | W10 Fri 11/12 | W10 Fri 11/12 | 6.1 SS+1d | No |
| 7.2 | Presentation / demo | W11 Mon 14/12 | W11 Fri 18/12 | 6.2 FS+1d | Yes |

Calendar critical-path analysis. A forward/backward pass over the durations and FS/SS/FF constraints in Table 4 gives zero calendar float for 1.1, 1.2, 2.1, 2.2, 2.3, 2.4, 3.1, 3.2, 3.5, 4.1, 4.2, 5.1, 4.3, 4.4, 5.2, 5.4, 6.3, 6.1, 6.2 and 7.2. Parallel critical branches exist for specification/mockups and test plan/test design. Tools setup (1.4) finished on 14/10 with two days of float; data design, UI/UX design, the W4 spike and the retrospective also have positive float. Zero float refers to the activity network with review and freeze time reserved, not to spare hours. The agreed availability in Section 4.3 covers the demand of this network.

Effort is not duration. For example, WBS 2.2 Requirements Specification requires 47 person-hours, while WBS 5.2 Must-have Features requires 94 person-hours. Their scheduled durations depend on parallel work, task dependencies, and confirmed team capacity rather than effort alone.

Schedule status. On 21/10/2026 all four members agreed to raise availability to 12 h/member/week in W4–W5, 13 h in W8 and 20 h in W9–W10, and to keep 10 h in W6–W7. With these hours no member-week in Section 4.5 is overloaded: W4–W5 provide 96 h for 88 h of demand and W8–W10 provide 212 h for 204 h. The added effort is a planning commitment, not an assumption of unlimited availability; R4 tracks it weekly.

## Roles and Responsibilities

| Role | Main | Backup | Responsibilities |
| --- | --- | --- | --- |
| Team lead / Project manager | A | C | Plan, assign tasks, weekly status report, contact point with the TA, Moodle submissions, presentation lead |
| Business analyst | B | A | Elicit and document requirements, organise reviews, traceability matrices, change log, AI usage log |
| Designer / Architect | C | D | Architecture, ADRs, class, data and UI design; consistency of diagrams and IDs across PAs |
| Developers | A, B, C, D | Module reviewer | Implement their modules (WBS 5.x), unit test, review other members' pull requests |
| Tester | D | B | Test plan, test cases, system testing, E2E and load tests, test report and defect log |
| DevOps (CI/CD, deployment) | D | B | Repository settings, CI pipeline, deployment, monitoring during the demo |

Table 5. Member codes used in this document

| Code | Full name | Student ID |
| --- | --- | --- |
| A | Lê Nguyễn Quốc Học | 24127044 |
| B | Thái Quang Huy | 24127177 |
| C | Trần Vũ Anh Kiệt | 24127196 |
| D | Nguyễn Văn Minh | 24127205 |

Each row lists the work packages a member executes in that week. Every work package is executed only by its owner in Table 2, so no package appears under two members. “Monitoring” is the member’s share of their own WBS 1.3 packages (A: 1.3.1–1.3.2; B: 1.3.3). Capacity is the availability agreed on 21/10/2026 (Section 4.3); no member-week is overloaded.

Weekly execution demand per member

| Wk | Member | Work packages (WBS ID: hours) | Need h | Avail. h | Gap h |
| --- | --- | --- | --- | --- | --- |
| W4 | A – Học | 2.2.1: 4 h; 2.2.2: 4 h; monitoring: 2 h | 10 | 12 | +2 |
| W4 | B – Huy | 2.1.1: 6 h; 2.1.2: 4 h; 2.2.5: 1 h; monitoring: 0.5 h | 11.5 | 12 | +0.5 |
| W4 | C – Kiệt | 2.2.3: 5 h; 2.3.1: 4 h; 2.2.8: 2 h | 11 | 12 | +1 |
| W4 | D – Minh | 3.1.4: 8 h; 2.2.4: 3 h | 11 | 12 | +1 |
| W5 | A – Học | 2.2.1: 2 h; 2.2.2: 3 h; 2.2.7: 5 h; monitoring: 1.5 h | 11.5 | 12 | +0.5 |
| W5 | B – Huy | 2.1.2: 1 h; 2.2.5: 4 h; 2.4.2: 5 h; monitoring: 1 h | 11 | 12 | +1 |
| W5 | C – Kiệt | 2.2.3: 1 h; 2.2.8: 2 h; 2.3.1: 4 h; 2.4.1: 4 h | 11 | 12 | +1 |
| W5 | D – Minh | 2.2.4: 4 h; 2.2.6: 7 h | 11 | 12 | +1 |
| W6 | A – Học | 3.2.2: 3 h; monitoring: 2 h | 5 | 10 | +5 |
| W6 | B – Huy | 3.2.1: 4 h; 3.2.3: 2 h; monitoring: 0.5 h | 6.5 | 10 | +3.5 |
| W6 | C – Kiệt | 3.1.1: 5 h; 3.1.2: 4 h; 3.4.1: 1 h | 10 | 10 | 0 |
| W6 | D – Minh | 3.1.3: 3 h; 3.3.1: 6 h | 9 | 10 | +1 |
| W7 | A – Học | 3.2.2: 3 h; 3.5.1: 5 h; monitoring: 1.5 h | 9.5 | 10 | +0.5 |
| W7 | B – Huy | 3.2.1: 3 h; 3.2.3: 3 h; monitoring: 1 h | 7 | 10 | +3 |
| W7 | C – Kiệt | 3.1.2: 2 h; 3.4.1: 6 h | 8 | 10 | +2 |
| W7 | D – Minh | 3.1.3: 3 h; 3.3.1: 2 h; 3.3.2: 5 h | 10 | 10 | 0 |
| W8 | A – Học | 4.2.1: 4 h; 4.3.1: 5 h; monitoring: 2 h | 11 | 13 | +2 |
| W8 | B – Huy | 4.2.2: 4 h; 4.4.1: 4 h; 5.1.2: 4 h; monitoring: 1 h | 13 | 13 | 0 |
| W8 | C – Kiệt | 4.3.3: 6 h; 5.1.1: 6 h | 12 | 13 | +1 |
| W8 | D – Minh | 4.1.1: 6 h; 4.3.2: 7 h | 13 | 13 | 0 |
| W9 | A – Học | 5.2.2: 6 h; 5.2.3: 7 h; 5.2.8: 4 h; monitoring: 1.5 h | 18.5 | 20 | +1.5 |
| W9 | B – Huy | 5.2.1: 8 h; 5.2.13: 5 h; 5.2.11: 5 h; monitoring: 0.5 h | 18.5 | 20 | +1.5 |
| W9 | C – Kiệt | 5.2.4: 6 h; 5.2.5: 9 h; 5.2.9: 4 h | 19 | 20 | +1 |
| W9 | D – Minh | 5.2.6: 8 h; 5.2.7: 9 h; 6.2.1: 3 h | 20 | 20 | 0 |
| W10 | A – Học | 5.2.8: 4 h; 6.2.2: 4 h; 6.3.1: 5 h; 7.1.1: 5 h; monitoring: 1.5 h | 19.5 | 20 | +0.5 |
| W10 | B – Huy | 5.2.11: 3 h; 5.2.12: 4 h; 6.1.2: 7 h; 6.1.3: 5 h; monitoring: 0.5 h | 19.5 | 20 | +0.5 |
| W10 | C – Kiệt | 5.2.9: 3 h; 5.2.10: 9 h; 5.4.1: 8 h | 20 | 20 | 0 |
| W10 | D - Minh | 5.4.2: 8 h; 6.1.1: 8 h; 6.2.1: 4 h | 20 | 20 | 0 |

Ownership changes only through the task board and is recorded in the weekly report and the Revision History. Main and backup roles were agreed in the PA0 team contract and are unchanged.

## Human Resources and Cost Estimate

The hypothetical labour rate is VND 70,000 per person-hour; labour contingency is 10%. Tools and deployment are budgeted on eligible no-cost plans, subject to quota and compatibility checks. The required scope includes a VND 100,000 reserve for authorised live payment testing. This is a planning allowance, not a quoted gateway fee or money already spent. The mock adapter used in CI has no transfer expense. Học records approval before any paid service or real-payment test.

Table 6. Required-scope estimate (F01–F08; F09/F10 excluded).

| Item | Basis | Cost (VND) |
| --- | --- | --- |
| Labour | 427 h × 70,000 | 29,890,000 |
| Tools | GitHub, Discord, Figma/draw.io: free plans | 0 |
| Hosting / static analysis | Eligible no-cost plans; quotas checked at setup | 0 |
| Payment test / demo budget | Reserve for live tests on the authorised channel | 100,000 |
| Contingency | 10% of labour | 2,989,000 |
| REQUIRED-SCOPE TOTAL |  | 32,979,000 |

Table 7. Alternative estimate if optional F09/F10 are also implemented.

| Item | Basis / assumption | Cost (VND) |
| --- | --- | --- |
| Labour (including optional) | 443 h × 70,000 | 31,010,000 |
| Tools / hosting / static analysis | As above | 0 |
| Payment test / demo budget | Reserve | 100,000 |
| Contingency | 10% of labour | 3,101,000 |
| FULL-SCOPE TOTAL |  | 34,211,000 |

The VND 100,000 test allowance is included once in each alternative budget. It is a provisional reserve, not a confirmed gateway fee. Returned test transfers are not net project expenditure; record unrecovered fees or test purchases. If eligible hosting, required live-channel access or the reserve is insufficient, Học seeks an explicit revised budget/delivery decision before spending.

Cost estimates measure hypothetical economic effort. Capacity is handled separately in the schedule-status decision in Section 4.3.

# Risk Management

Risk assessment. Probability P: 0.1 (very unlikely) to 0.9 (very likely); loss L: 1 (negligible) to 10 (project failure). RE = P × L. Risks are ordered by descending RE; IDs remain stable for tracking. Review RE ≥ 3.0 weekly and other risks at each phase gate, or sooner if triggered. Owners record actions, due dates and revised scores in weekly reports.

Risk ownership follows the PA0 roles: Học (PM), Huy (BA), Kiệt (Architect) and Minh (Tester/DevOps); all four also develop software. Risk scores are planning assessments, reviewed weekly or when triggered. Minh executes the W4 payment/concurrency spike (WBS 3.1.4), and Kiệt reviews its design and results.

| ID | Risk | Type | Probability | Loss | RE | Mitigation / contingency | Owner |
| --- | --- | --- | --- | --- | --- | --- | --- |
| R4 | Failure to sustain the increased weekly availability agreed in Section 4.3, or member absence, may delay delivery or compress Must-have testing and documentation. | People / estimation | 0.6 | 8 | 4.8 | Mitigation: each member logs actual hours on GitHub issues; weekly reports compare them with the agreed 12 h in W4–W5, 13 h in W8 and 20 h in W9–W10. PA5 foundation work (WBS 5.1) starts after the PA3 gate. Contingency: if a member misses the agreed hours for two consecutive weeks, Học escalates to the TA and the team records a scope or schedule decision. Preserve Must-have tests and continue weekly risk monitoring. | Lê Nguyễn Quốc Học |
| R1 | A member cannot explain AI-generated code or text, allowing defects or unsupported claims into a submission. | People / quality | 0.5 | 8 | 4.0 | Mitigation: require owner and peer verification, AI logs and walkthroughs. Contingency: block unexplained work from submission, pair-review and rewrite it; repeat relevant checks and update the log with actual verification. | Thái Quang Huy |
| R2 | Duplicate callbacks or concurrent purchase/expiry processing issue duplicate tickets or exceed event capacity. | Technology | 0.4 | 9 | 3.6 | Mitigation: W4 tests cover concurrency, repeated callbacks and late payments; use atomic capacity updates, idempotency and unique ticket issuance. Contingency: pause affected sales; flag exceptions as pending reconciliation, retaining evidence and preventing duplicate processing. For paid tickets, issue only after verifying payment and available capacity. Free tickets bypass payment but remain subject to capacity and duplicate-issuance controls. Kiệt coordinates technical resolution; Học liaises with the organiser/account holder. Record the completed resolution and payer notification before closure; stopping issuance alone is not resolution. | Trần Vũ Anh Kiệt |
| R3 | Delayed payOS access or invalid/missing webhooks prevent payment confirmation and QR ticket delivery. | Technology | 0.4 | 8 | 3.2 | Mitigation: Minh verifies one authorised payOS channel, signatures, callback matching and expiry in the W4 spike (WBS 3.1.4), and Kiệt reviews the spike result. Học confirms the account holder, TA permission, exception ownership and payer communication before transfers. Contingency: use a clearly labelled mock for continued development/CI, retain payment evidence and escalate blocked live acceptance. Mock results do not complete the live-channel commitment; a changed PA5 boundary requires an explicit TA/team decision. No automated refunds or custody of funds are included. | Trần Vũ Anh Kiệt |
| R5 | Exposed secrets or participant records enable unauthorised access or disclosure of personal data. | Security / privacy | 0.3 | 9 | 2.7 | Mitigation: exclude secrets from Git and AI prompts; use synthetic data and review access controls. Contingency: revoke credentials, contain access, assess affected records and notify the team lead; remove exposed data and review the cause. | Nguyễn Văn Minh |
| R6 | Hosting, email or another external service outage interrupts ticket delivery or the live demo. | Technology | 0.3 | 8 | 2.4 | Mitigation: check service health and rehearse a local demo with synthetic data; prepare a backup video. Contingency: identify the fallback as such, restore service and retry email delivery for the same ticket, without creating another entitlement. | Nguyễn Văn Minh |
| R7 | Lost connectivity, denied camera access or incompatible devices stop QR check-in and cause queues. | Technology | 0.3 | 7 | 2.1 | Mitigation: test HTTPS camera access and supported phones; prepare a backup device and network. Contingency: switch device/network; pause admissions until server validation returns, then reject invalid or used tickets. Do not bypass validation with offline admission. | Nguyễn Văn Minh |
| R8 | New requests or Should-have work consume time needed to implement and test F01–F08. | Scope | 0.4 | 5 | 2.0 | Mitigation: assess each change against PA0, effort and dependencies with the team lead. Contingency: defer F09–F10 or new requests, record the decision and revise the plan while preserving Must-have implementation, tests and review. | Thái Quang Huy |
| R9 | Requirements based on limited survey sources miss other clubs’ workflows, causing unsuitable rules and rework. | Requirements | 0.4 | 4 | 1.6 | Mitigation: compare other clubs’ event information and interview additional organisers in PA2; record assumptions. Contingency: revise affected requirements and traceability, obtain stakeholder feedback and agree a bounded workflow before implementation. | Thái Quang Huy |

Shaded rows have RE ≥ 3.0 and require weekly review; other risks are reviewed at phase gates or sooner if triggered. The revised availability covers planned demand; R4 remains open to monitor delivery against that commitment. F01–F08 remain Must-have; F09–F10 remain Should-have.

# Tools & Collaboration Setup

PA0 working rules remain in force. The verification record below distinguishes configuration observed on 21 October 2026 from checks that require team or TA confirmation. Repository evidence was read directly; README statements alone are not treated as proof of enforcement. Application CI is a later WBS 5.1.2 milestone.

- Moodle - course announcements and PA submissions. Lê Nguyễn Quốc Học submits the required files; Trần Vũ Anh Kiệt is the PA0 backup. Retain the submitted version, source and submission confirmation according to course requirements.

- Communication - Discord server "UniEvent - T07": https://discord.gg/zVMjhEGnzp. The TA confirmed that membership in the team's Discord server is not required. Use Discord for discussion and reviews; record decisions and action owners in weekly reports and linked issues. Respond within 12 hours on weekdays and 24 hours at weekends.

- Task board - GitHub Projects “Team Management”: https://github.com/orgs/UniEvent-T07/projects/1. PA1 issues #29–#32 cover Sections 2–6. Học confirms one assignee and the actual due date for each issue before submission; due dates for #31 and #32 remain pending verification. From W4, each Level-3 work package is to have an issue matching Table 2: WBS ID, one executing owner, estimate, week, output, due date, status and evidence links. Học checks full WBS coverage before submission and maintains it weekly. States: Backlog, To do, In progress, In review, Done. Shared-document review evidence is acceptable for PA1 section tasks.

- Git repository - https://github.com/UniEvent-T07/UniEvent. The repository and default branch main were verified on 21 October 2026. README, .gitignore, issue/PR templates and the core documentation/source folders exist. The PA1 application stack is selected as in Section 3.2. Học records the instructor/TA account and confirms repository access before submission; this check remains pending.

  - The active “Protect main” ruleset was verified on 21 October 2026: it targets the default branch, requires a pull request with one approving review, dismisses stale approvals after new commits, requires resolution of review threads, and blocks deletion and non-fast-forward updates. It has no listed bypass actors. Evidence: https://github.com/UniEvent-T07/UniEvent/rules/25001815. Application lint/build/test checks are not in the observed ruleset; Huy adds the CI and required status checks under WBS 5.1.2 before the first Must-have implementation merge, then records a failing PR blocked and a passing PR accepted.

  - Proposed branch convention: type/issue-short-description; PRs link the task, relevant requirement IDs and verification evidence. Definition of Done for documents: complete content, review by another member, resolved feedback and updated traceability. For application code: acceptance criteria met, appropriate tests recorded, peer approval, required CI checks passed and related documentation updated. Manual checks during setup do not waive the CI milestone for Must-have implementation; if it is missed, keep the PR unmerged and escalate to Học.

  - README, .gitignore and issue/PR templates were observed in main on 21 October 2026. The .gitignore excludes .env/.env.*, keys, build output and test artefacts while permitting .env.example. Add sample-only .env.example files with the application foundation under WBS 5.1.2. Real credentials remain outside Git and AI prompts; use deployment secret settings and synthetic test data. The observed issue-to-Discord workflow is notification automation and does not establish application CI or current Discord delivery.

  - Use Conventional Commits (feat:, fix:, docs:, test:, refactor:, chore:). PA1 owners edit the shared document and reviewers leave comments/suggestions; separate section PRs are unnecessary. Finish individual work 2 days before the PA deadline; the lead integrates and freezes the reviewed version 1 day before it. Commit the final PDF and source to /pa/PA1 through a reviewed PR before Moodle submission.

  - Record significant AI use in /docs/ai-usage/PAx.md, including this PA1 revision; Thái Quang Huy consolidates entries. Each owner records the actual purpose, human checks and corrections, and must explain the result; another member verifies it. Keep the phase log consistent with the document AI Usage Log. Do not claim review merely because AI suggests it; exclude secrets, real payment data and third-party personal data.

- Weekly status meeting with the TA: Thursday 20:00–20:15 (attendance to confirm). Internal meetings: Tuesday 21:00–21:45 and Saturday 21:00–21:30. Submit the weekly status report for W2–W10 to /docs/management/weekly/W<week>-status.md. Deadline: Sunday 22:00 (GMT+7). All meeting times are GMT+7. Record progress, blockers, risks and decisions; preserve previous reports and document corrections in the next report. Give at least 12 hours notice of absence. Seek consensus, then vote after 24 hours if needed; the lead breaks ties.

Evidence owners and deadlines: Học closes the PA1 contribution confirmation, board coverage/due-date checks and TA access/membership checks before submission. Huy maintains the repository/ruleset record and provides application CI evidence at WBS 5.1.2; Minh owns deployment evidence at WBS 6.2.1. Huy reconciles the AI log. An open item is not marked complete without direct evidence; invitations alone do not prove membership. Keep the setup record and linked PA1 issues consistent.

PA1 setup verification record — checked 21 October 2026

Evidence links: main repository tree | main protection | W3 status report

| Item | Status | Evidence / next action | Check / deadline |
| --- | --- | --- | --- |
| Repository and initial files | Verified | main tree, README, .gitignore and issue/PR templates | 21 Oct; connector read |
| Main protection / peer review | Verified | Active Protect main ruleset, #25001815; one approval; no bypass actors | 21 Oct; connector read |
| PA1 tasks / full WBS coverage | Partial | Học confirms PA1 assignees/due dates and full WBS coverage; Level-3 issue details follow Table 2. | Before submission |
| TA Discord membership | – Not required | Invite URL is recorded; current delivery and TA membership need direct confirmation (Học) | Before submission |
| Instructor/TA repository access | Not required | Học records the actual accounts and access check; no account is assumed | Before submission |
| Weekly reports | Files verified | W2-status.md and W3-Status.md exist; timeliness not independently checked | 21 Oct; connector read |
| Application quality CI | Planned | No lint/build/test workflow in the inspected main tree; Huy implements WBS 5.1.2 | Before first feature merge |

Repository structure: existence checked in main on 21 October 2026; delivery contents follow their phase gates

| Folder | Content |
| --- | --- |
| /src | Exists: /src/README.md. Application code is added with WBS 5.1; planned layout /src/web and /src/api follows the selected stack. |
| /docs/management | Exists: /docs/management/weekly, including W2-status.md and W3-Status.md. Học standardises W3-Status.md to W3-status.md and updates links after the rename. |
| /docs/devops | Exists: task-notifications.md describing the issue-to-Discord automation. |
| /docs/guides | Exists: Vietnamese team guides for Discord and GitHub Projects. |
| /docs/requirements | Exists with README. PA2 adds the SRS, use cases, mockups, glossary, traceability and interview notes; Huy checks the PA2 gate. |
| /docs/design | Exists with README. PA3 adds C4/UML models, ERD and ADRs; Kiệt checks the design baseline. |
| /docs/test | Exists with README. PA4 adds test plans/cases; PA5 adds execution reports and defect evidence; Minh checks each gate. |
| /docs/ai-usage | Exists: PA0.md and PA1.md. Huy reconciles the repository PA1 log with this document before submission. |
| /pa/PA1 ... /pa/PA5 | /pa/PA0 exists with PDF/source. /pa/PA1 through /pa/PA5 were not present in the inspected tree. Học creates each phase folder and commits its matching reviewed PDF/source before submission. |
| /.github | Exists: issue template, PR template, team.json, scripts/issue-to-discord.mjs and the issue-discord.yml notification workflow. Huy implements required application lint/build/test CI under WBS 5.1.2. |
| /scripts | Root-level helper scripts are optional; the existing notification script is in /.github/scripts. The implementing owner documents and peer-reviews scripts before use. |

# AI Usage Log

| # | Member | Tool | Task / purpose | How the output was verified and changed |
| --- | --- | --- | --- | --- |
| 1 | Lê Nguyễn Quốc Học | ChatGPT (OpenAI) | Assisted in planning and drafting Section 4 (Project Plan), including WBS, effort estimation, schedule, roles, and cost analysis. | Reviewed AI-generated planning suggestions against the course rubric and PA0. Cross-checked WBS IDs, effort estimates, dependencies, and team capacity; identified inconsistencies for revision. |
| 2 | Lê Nguyễn Quốc Học | ChatGPT (OpenAI) | Reviewed PA1 against the course rubric, PA0 baseline, and official template to identify missing content and inconsistencies. | AI identified discrepancies in WBS IDs, effort estimates, and schedule dependencies. Findings were marked for manual verification and correction. |
| 3 | Lê Nguyễn Quốc Học | ChatGPT (OpenAI) | Evaluated the consistency and feasibility of the WBS, effort estimates, project schedule, and resource allocation. | AI highlighted inconsistent work-package references, dependency issues, and a capacity shortfall. Recommendations were considered for revising the project plan. |
| 4 | Lê Nguyễn Quốc Học | ChatGPT / Codex (OpenAI) | 21 October 2026: revised PA1 text, payment boundary, capacity reconciliation, contributor hours, target schedule/Gantt, setup evidence and costs; prepared the updated Word file for the original Drive record. | User confirmed the selected stack, one live payOS channel and retention of PA0 hours. AI checked WBS/resource sums, read repository/ruleset/report evidence and rendered the revised layout. All-member percentages, TA access, merchant authorisation and capacity recovery remain pending human confirmation; no additional completed review is claimed. |
| 5 | Nguyễn Văn Minh | ChatGPT / Codex (OpenAI) | Drafted and iteratively revised Sections 5–6 using PA0 and the PA1 template; compared V3 with earlier drafts; reviewed risk scoring/owners, payment exceptions and collaboration/CI rules. On 21 October 2026, checked alignment with the updated Section 4 and prepared this log entry. | Minh supplied references, clarified ownership and formatting constraints, and requested successive reviews and corrections. Revisions distinguished free/paid tickets, clarified payment-exception closure and CI deadlines, and preserved the template. AI recalculated RE, checked WBS/capacity links and rendered/compared the DOCX. The latest check matched the 8 h W4–W5 and 55 h W8–W10 deficits to R4. Human/peer approval and capacity recovery remain pending; this entry does not claim that Minh tested the application or configured repository/Discord settings through these sessions. |
| 6 | Thái Quang Huy | ChatGPT (OpenAI) | Used ChatGPT to review the UniEvent PA1 proposal against the original document, GitHub repository, PA1 template, and course guidelines. Requested checks of the Vision, proposed architecture, feature scope, WBS, effort estimates, Gantt schedule, resource feasibility, cost calculations, risks, and collaboration setup. ChatGPT identified inconsistencies, suggested corrections, and produced separate revised reference documents. | Requested multiple review iterations instead of accepting the first output. ChatGPT cross-checked WBS identifiers, effort totals (422 required hours and 438 hours including optional work), cost calculations, and repository evidence. Unresolved issues, including schedule feasibility and contribution evidence, were explicitly identified for team confirmation. |
| 7 | Thái Quang Huy | ChatGPT (OpenAI) | Used ChatGPT to analyse 22 historical PA1 evaluation comments from Intro2SE class 24C05 and compare them with UniEvent PA1 and the course grading rubric. Requested improvements to actor-specific problem analysis, stakeholder responsibilities, access permissions, data ownership, work-package accountability, revision tracking, and completeness of required sections. ChatGPT prepared the PA1 V2 reference document and a feedback-comparison report. | Requested further checks against the original PA1 template and grading criteria. ChatGPT revised the proposed content to address relevant historical feedback and identified remaining limitations. Stakeholder assumptions, individual contributions, and the project's critical path were not treated as independently validated. |
| 8 | Thái Quang Huy | ChatGPT (OpenAI) | Used ChatGPT to perform an additional review of PA1 V2, refine the content, and prepare PA1 V3 as a reference for team members to copy into the shared PA1 document. Clarified that the team collaboratively edits one Google Drive document and tracks PA1 through GitHub Project issues rather than separate pull requests for each section. Requested formatting alignment with the original template, updated tables, and a section-by-section handoff guide. | ChatGPT compared the revised document with the original template, checked the exported document structure (26 tables and 3 embedded figures), reviewed pagination, and updated the reference document's table of contents. It also highlighted the unresolved W9–W10 resource deficit, Gantt/critical-path validation, and pending contribution and AI-log evidence. The original shared PA1 document was not overwritten by ChatGPT; final content acceptance and submission remain the team's responsibility. |
| 9 | Thái Quang Huy | Claude (Anthropic) | 21/10/2026: reviewed PA1 against 22 historical PA1 comments from class 24C05, PA0 and the repository; proposed one-owner work allocation, per-problem and per-user Vision tables, organisation administration (F01, WBS 5.2.13), calendar dates and corrected costs; regenerated Figure 3. | Claude recomputed every WBS, capacity and cost total with scripts and checked each work package against the weekly allocation. The member checked each change against the template; the capacity option (B) and contribution percentages were decided by the whole team on 21/10/2026. |